## CONTG 4TH Q
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
Continuing Appropriation
As of 4TH QUARTER, CY 2019
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development:
Purchase of Land for Relocation and Evacuation |  | 444945 |  |  |  | 0
Repair and Rehab of Brgy Roads |  | 494062.14 |  |  |  | 231252.56
Const. of Multi-Purpose Hall for OSY |  | 500000 |  |  |  | 0
BIARPS/ARISP/ARCDP/FMR & SCH. BLDG. |  | 670101.75 |  |  |  | 495200
COMPLETION OF KC-NCDDP MP BLDG-CAGAWASAN |  | 200000 |  |  |  | 200000
Installation and Maintenance of Lighting |  | 90416.37 |  |  |  | 85243.52
Rep. and Rehab. of Mun. Road |  | 3916.74 |  |  |  | 3916.74
Counterpart to KALAHI-NCDDP |  | 85241.66 |  |  |  | 0
Counterpart to BUB/GPB/ADM Project |  | 50000 |  |  |  | 0
DA/DENR Counterpart |  | 496385.4 |  |  |  | 0
Purchase of Motor Grader |  | 13545194 |  |  |  | 13540194
Loan Amortization-LOGOFIND |  | 1069352.66 |  |  |  | 1096669.98
KOICA-Integrated Modern Rice Processing Complex |  | 106489.04 |  |  |  | 0
BUB 2014-16 Counterpart |  | 44487.95 |  |  |  | 0
Construction of Multi-Purpose Building |  | 200000 |  |  |  | 0
|  | 18000592.71 |  |  |  | 15652476.8
Economic Development:
Improvement of San Isidro Public Market |  | 552270.36 |  |  |  | 494528.2
Improvement and Rehab. of Public Market Access Roads |  | 2447272 |  |  |  | 2245027.1
Improvement of Bus Terminal |  | 32891.6 |  |  |  | 32891.6
Rehabilitation of 3 Markets |  | 1953.02 |  |  |  | 1953.02
Improvement of Public Markets |  | 37404 |  |  |  | 37404
Loan Amortization -CBRMP |  | 140535.56 |  |  |  | 305233.73
Loan Amortization - Land Bank |  | 1885462.87
|  | 5097789.41 |  |  |  | 3117037.65
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
Continuing Appropriation
As of 4TH QUARTER, CY 2019
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Environmental Management:
Ecological/Environmental Services |  | 243821 |  |  |  | 0
LGSP-LED Equity |  | 50000 |  |  |  | 0
Landcare Program |  | 27320 |  |  |  | 17150
Integrated Solid Waste Management |  | 44030.86 |  |  |  | 12650
ICRAF-Environment and Natural Resources |  | 49358 |  |  |  | 0
PILAR DAM Program |  | 1002 |  |  |  | 0
Procurement of Mechanical/Solar Power Generator |  | 2840000 |  |  |  | 0
|  | 3255531.86 |  |  |  | 29800
|  | 26353913.98 |  |  |  | 18799314.45 |  |  | 71.33%
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ELAINE E. RESUSTA |  |  |  |  | NECITAS T. CUBRADO
Municipal Budget Officer |  |  |  |  | LCE

## 4TH Q CURRENT
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
Current Legislative Appropriation
As of 4TH QUARTER, CY 2019
Province, City or Municipality: PILAR, BOHOL
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development:
Installation & Maintenance of Street Lighting |  | 450000 |  |  |  | 407242.85
Repair and Maintenance of Municipal Roads |  | 200000 |  |  |  | 157444.58
BIARPS/ARCDP/ARISP/FMR/LOGOFIND Bldg. Maintenance |  | 330000 |  |  |  | 265575
Repair and Rehabilitation of Barangay Roads |  | 1050000 |  |  |  | 786161.5
Loan Amortization (CBRMP & LOGOFIND) |  | 50000 |  |  |  | 24162.61
KALAHI Counterpart Contribution |  | 2100000 |  |  |  | 2100000
DA/DENR Counterpart |  | 150000 |  |  |  | 0
Municipal Circumferential Road Concreting |  | 700000 |  |  |  | 540440
Rural Electrification Project |  | 200000 |  |  |  | 98000
Improvement of Municipal Ground |  | 100000 |  |  |  | 0
Multi-purpose Hall |  | 1000000 |  |  |  | 0
Completion of Cultural Facility |  | 200000 |  |  |  | 129582
Construction of Heavy Equipment Multi-purpose Building |  | 300000 |  |  |  | 0
Rehabilitation of Bayong to San Vicente Road (Purok 4 to Purok 6 Bayong Section) |  | 300000 |  |  |  | 156250
|  | 7130000 |  |  |  | 4664858.54
Economic Development:
Purchase of Heavy Equipment (Backhoe) |  | 10205656.6 |  |  |  | 10205656.6
Bagumbayan Public Market Improvement |  | 800000 |  |  |  | 42500
Poblacion Public Market Improvement |  | 350000 |  |  |  | 83300
Improvement of San Isidro Public Market |  | 350000 |  |  |  | 0
Sagnap Spring Eco-tourism Improvement |  | 500000 |  |  |  | 0
Construction ESKAYA Cultural Heritage Development Learning Center |  | 500000 |  |  |  | 0
Improvement of Block Tienda at Malinao Dam/Freedom Park |  | 200000 |  |  |  | 0
|  | 12905656.6 |  |  |  | 10331456.6
Environmental Management:
Ecological and Environmental Services |  | 105706.8 |  |  |  | 0
|  | 105706.8 |  |  |  | 0
|  | 20141363.4 |  |  |  | 14996315.14 |  |  | 74.46%
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ELAINE E. RESUSTA | [5 empty] | NECITAS T. CUBRADO
Municipal Budget Officer | [5 empty] | LCE
0