## 2nd Quarter
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
Current Legislative Appropriation
As of 2ND QUARTER, CY 2020
Province, City or Municipality: PILAR, BOHOL
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development:
Installation & Maintenance of Street Lighting |  | 300000 |  |  |  | 103102.5
Municipal Circumferential Road Concreting |  | 800000 |  |  |  | 11350
Rural Electrification Project |  | 300000 |  |  |  | 0
Multi-Purpose Hall |  | 200000 |  |  |  | 0
Repair and Maintenance of Municipal Roads |  | 400000 |  |  |  | 64733.66
Completion of Cultural Facility |  | 1000000 |  |  |  | 0
Construction of Heavy Equipment Multi-Purpose Building |  | 700000 |  |  |  | 0
Rehabilitation of Bayong to San Vicente Road (Purok 4 to Purok 6 Bayong Section) |  | 300000 |  |  |  | 0
Purok 2 Inaghuban (Road Opening) |  | 181742 |  |  |  | 0
Repair and Rehabilitation of Barangay Roads |  | 2100000 |  |  |  | 334550
KALAHI Counterpart Contribution |  | 2100000 |  |  |  | 0
BIARPS/ARCDP/ARISP/FMR/LOGOFIND Bldg. Maintenance |  | 330000 |  |  |  | 0
Loan Amortization (CBRMP & LOGOFIND) |  | 1450000 |  |  |  | 713033.16
DA/DENR Counterpart |  | 150000 |  |  |  | 0
Counterpart for AM Projects |  | 200000 |  |  |  | 0
Improvement of Municipal Ground |  | 200000 |  |  |  | 0
Sub-total |  | 10711742 |  |  |  | 1226769.32
Economic Development:
Bagumbayan Public Market Improvement |  | 500000 |  |  |  | 0
Poblacion Public Market Improvement |  | 650000 |  |  |  | 0
Improvement of San Isidro Market |  | 500000 |  |  |  | 0
Tourism Development |  | 100000 |  |  |  | 0
Construction ESKAYA Cultural Heritage Development Learning Center |  | 200000 |  |  |  | 0
Slaughterhouse Bagumbayan |  | 1200000 |  |  |  | 0
Improvement of LGU Center (Water Facilities) |  | 300000 |  |  |  | 0
Purchase of Heavy Equipment (Roadroller Vibrator/Compactor) |  | 2000000 |  |  |  | 0
Sub-total |  | 5450000 |  |  |  | 0
Environmental Management:
Ecological and Environmet Services |  | 106000.4 |  |  |  | 0
Sanitary Landfill Counterpart Contribution |  | 700000 |  |  |  | 0
Sub-total |  | 806000.4 |  |  |  | 0
GRAND TOTAL |  | 16967742.4 |  |  |  | 1226769.32
#DIV/0!
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
RAYMUND B. ANANIA | [5 empty] | NECITAS T. CUBRADO
Municipal Budget Officer - Designate | [5 empty] | Local Chief Executive
14996315.14