## 3rd qtr (hidden)
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE THIRD QUARTER, CY 2016
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
Pilar GYMP | Pilar, Bohol | 1200000 |  | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 |  | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-10 | 2015-10-10 | 100% | 175135.26 |  | 64864.74 |  | completed | 64394.74
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-10 |  | 100% | 62783.19 |  | 7216.81 |  | completed | 6419.29
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-10 |  | 100% | 90424.26 |  | 9575.74 |  | completed | 8700.74
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-10 |  | 100% | 103217.52 |  | 16782.48 |  | completed | 16360.68
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-10 |  | 100% | 217936.06 |  | 22063.94 |  | completed | 20860.49
Sub-Total |  | 770000 | 766232.23 |  |  |  | 649496.29 |  | 120503.71
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 93.5% | 93436.84 |  | 6563.16 |  | on-going | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 222483.04 |  | 37516.96 |  | completed | 37480.88
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 712185.22 | 37480.88 | 37814.78
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 79.16% | 94480.7 | 24873 | 25519.3 |  | on-going | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-22 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-22 | 2015-11-22 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-22 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-02-24 | 100% | 10988890.45 |  | 373106.44 |  | completed | 363075.35
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 41766237.74 |  | 381647.09
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48162421.46 |  | 799888.64
0
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed | 0
Total |  | 9711209.04 | 9626189.49 |  |  |  | 9626189.49 |  | 85019.55
Certified Correct: | [6 empty] | Approved by:
ELAINE E. RESUSTA, CPA | [8 empty] | HON. NECITAS T. CUBRADO
Municipal Accountant- Designate | [8 empty] | Municipal Mayor

## 4th qtr (hidden)
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FOURTH QUARTER, CY 2016
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
Pilar GYMP | Pilar, Bohol | 1200000 |  | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 |  | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-10 | 2015-10-10 | 100% | 175135.26 |  | 64864.74 |  | completed | 64394.74
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-10 |  | 100% | 62783.19 |  | 7216.81 |  | completed | 6419.29
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-10 |  | 100% | 90424.26 |  | 9575.74 |  | completed | 8700.74
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-10 |  | 100% | 103217.52 |  | 16782.48 |  | completed | 16360.68
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-10 |  | 100% | 217936.06 |  | 22063.94 |  | completed | 20860.49
Sub-Total |  | 770000 | 766232.23 |  |  |  | 649496.29 |  | 120503.71
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 100% | 93436.84 |  | 6563.16 |  | on-going | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 222483.04 |  | 37516.96 |  | completed | 37480.88
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 712185.22 | 37480.88 | 37814.78
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 100% | 94480.7 | 24873 | 25519.3 |  | on-going | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-22 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-22 | 2015-11-22 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-22 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-02-24 | 100% | 11318045.2 |  | 43951.69 |  | completed | 33920.6
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 42095392.49 |  | 52492.34
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48491576.21 |  | 470733.89
BUB Projects
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed
Rehabilitation/ Upgrading of Level III Water Supply/ including Water Treatment |  | 7360000 | [6 empty] | 7360000 |  | OR# 0412316 dated September 1, 2016; v# 094 | 0
Construction of Evacuation Facility CY 2016 |  | 12000000 | [6 empty] | 12000000 |  | or# 0412317 dated September 1, 2016; v# 094 | 0
Total BUB Projects |  | 29071209.04 | 9626189.49 |  |  |  | 9626189.49 |  | 19445019.55
Other project Funded by NGA
Construction of Early Childhood Care and Development Council Building |  | 2300000 | [6 empty] | 2300000 |  | or# 0414328 dated November 17, 2016 v# 121 | 0
Certified Correct: | [6 empty] | Approved by:
ELAINE E. RESUSTA, CPA | [8 empty] | HON. NECITAS T. CUBRADO
Municipal Accountant- Designate | [8 empty] | Municipal Mayor

## 1st qtr 2017 (hidden)
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FIRST QUARTER, CY 2016
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
Pilar GYMP | Pilar, Bohol | 1200000 |  | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 |  | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-10 | 2015-10-10 | 100% | 175135.26 |  | 64864.74 |  | completed | 64394.74
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-10 |  | 100% | 62783.19 |  | 7216.81 |  | completed | 6419.29
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-10 |  | 100% | 90424.26 |  | 9575.74 |  | completed | 8700.74
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-10 |  | 100% | 103217.52 |  | 16782.48 |  | completed | 16360.68
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-10 |  | 100% | 217936.06 |  | 22063.94 |  | completed | 20860.49
Sub-Total |  | 770000 | 766232.23 |  |  |  | 649496.29 |  | 120503.71
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 100% | 93436.84 |  | 6563.16 |  | on-going | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 222483.04 |  | 37516.96 |  | completed | 37480.88
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 712185.22 | 37480.88 | 37814.78
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 100% | 94480.7 | 24873 | 25519.3 |  | on-going | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-22 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-22 | 2015-11-22 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-22 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-02-24 | 100% | 11318045.2 |  | 43951.69 |  | completed | 33920.6
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 42095392.49 |  | 52492.34
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48491576.21 |  | 470733.89
BUB Projects
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed
Rehabilitation/ Upgrading of Level III Water Supply/ including Water Treatment |  | 7360000 | [6 empty] | 7360000 |  | detailed estimates subject for approval and go signal from DILG Regional Office | 0
Construction of Evacuation Facility CY 2016 |  | 12000000 | [6 empty] | 12000000 |  | detailed estimates subject for approval and go signal from DILG Regional Office | 0
Total BUB Projects |  | 29071209.04 | 9626189.49 |  |  |  | 9626189.49 |  | 19445019.55
Other project Funded by NGA
Construction of Early Childhood Care and Development Council Building |  | 2300000 |  |  |  |  | 956718.59 |  | 1343281.41 |  | on-going | -956718.59
Certified Correct: | [6 empty] | Approved by:
ELAINE E. RESUSTA, CPA | [8 empty] | HON. NECITAS T. CUBRADO
Municipal Accountant- Designate | [8 empty] | Municipal Mayor

## 2nd qtr 2017 (hidden)
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE SECOND QUARTER, CY 2017
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
Pilar GYMP | Pilar, Bohol | 1200000 |  | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 |  | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-10 | 2015-10-10 | 100% | 175135.26 |  | 64864.74 |  | completed | 64394.74
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-10 |  | 100% | 62783.19 |  | 7216.81 |  | completed | 6419.29
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-10 |  | 100% | 90424.26 |  | 9575.74 |  | completed | 8700.74
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-10 |  | 100% | 103217.52 |  | 16782.48 |  | completed | 16360.68
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-10 |  | 100% | 217936.06 |  | 22063.94 |  | completed | 20860.49
Sub-Total |  | 770000 | 766232.23 |  |  |  | 649496.29 |  | 120503.71
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 100% | 93436.84 |  | 6563.16 |  | on-going | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 222483.04 |  | 37516.96 |  | completed | 37480.88
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 712185.22 | 37480.88 | 37814.78
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 100% | 94480.7 | 24873 | 25519.3 |  | on-going | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-22 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-22 | 2015-11-22 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-22 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-02-24 | 100% | 11351965.8 |  | 10031.09 |  | completed | 0
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 42129313.09 |  | 18571.74
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48525496.81 |  | 436813.29
BUB Projects
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed
Rehabilitation/ Upgrading of Level III Water Supply/ including Water Treatment |  | 7360000 | 10298810.26 |  |  |  | 0 |  | 7360000 |  | on-going | 10298810.26
Construction of Evacuation Facility CY 2016 |  | 12000000 | 19997000 |  |  |  | 0 |  | 12000000 |  | on-going | 19997000
Total BUB Projects |  | 29071209.04 | 39921999.75 |  |  |  | 9626189.49 |  | 19445019.55
Other project Funded by NGA
Construction of Early Childhood Care and Development Council Building |  | 2300000 | 2437900 |  |  | 95% | 2300000 |  | 0 |  | on-going | 137900
Certified Correct: | [6 empty] | Approved by:
ELAINE E. RESUSTA, CPA | [8 empty] | HON. NECITAS T. CUBRADO
Municipal Accountant- Designate | [8 empty] | Municipal Mayor

## 3rd qtr 2017 (hidden)
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE THIRD QUARTER, CY 2017
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
Pilar GYMP | Pilar, Bohol | 1200000 |  | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 |  | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
Construction of MDRRMC Building (Phase IV) | Poblacion, Pilar, Bohol | 1395500 | 1395500 | 2017-08-04 | 2017-12-02 | 76.86% | 1072609.45 |  | 322890.55 |  | on going
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-10 | 2015-10-10 | 100% | 175135.26 |  | 64864.74 |  | completed | 64394.74
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-10 |  | 100% | 62783.19 |  | 7216.81 |  | completed | 6419.29
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-10 |  | 100% | 90424.26 |  | 9575.74 |  | completed | 8700.74
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-10 |  | 100% | 103217.52 |  | 16782.48 |  | completed | 16360.68
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-10 |  | 100% | 217936.06 |  | 22063.94 |  | completed | 20860.49
Sub-Total |  | 770000 | 766232.23 |  |  |  | 649496.29 |  | 120503.71
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 100% | 93436.84 |  | 6563.16 |  | on-going | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 222483.04 |  | 37516.96 |  | completed | 37480.88
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 712185.22 | 37480.88 | 37814.78
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 100% | 94480.7 | 24873 | 25519.3 |  | on-going | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-22 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-22 | 2015-11-22 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-22 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-02-24 | 100% | 11351965.8 |  | 10031.09 |  | completed | 0
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 42129313.09 |  | 18571.74
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48525496.81 |  | 436813.29
BUB Projects
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed
Rehabilitation/ Upgrading of Level III Water Supply/ including Water Treatment |  | 10300000 | 10298810.26 |  |  | 92.96% | 7212611.88 |  | 3087388.12 |  | on-going | 3086198.38
Construction of Evacuation Facility CY 2016 |  | 12000000 | 19997000 |  |  | 66.47% | 8438408.46 |  | 3561591.54 |  | on-going | 11558591.54
Total BUB Projects |  | 32011209.04 | 39921999.75 |  |  |  | 25277209.83 |  | 6733999.21
Other project Funded by NGA
Construction of Early Childhood Care and Development Council Building |  | 2300000 | 2437900 |  |  | 100% | 2300000 |  | 0 |  | completed | 137900
Certified Correct: | [6 empty] | Approved by:
ELAINE E. RESUSTA, CPA | [8 empty] | EUGENIO B. DATAHAN II
Municipal Accountant- Designate | [8 empty] | Municipal Mayor

## 4th qtr 2017 (hidden)
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE FOURTH QUARTER, CY 2017
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
Pilar GYMP | Pilar, Bohol | 1200000 |  | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 |  | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
Construction of MDRRMC Building (Phase IV) | Poblacion, Pilar, Bohol | 1395500 | 1395500 | 2017-08-04 | 2017-12-02 | 76.86% | 1072609.45 |  | 322890.55 |  | on going
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-10 | 2015-10-10 | 100% | 175135.26 |  | 64864.74 |  | completed | 64394.74
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-10 |  | 100% | 62783.19 |  | 7216.81 |  | completed | 6419.29
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-10 |  | 100% | 90424.26 |  | 9575.74 |  | completed | 8700.74
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-10 |  | 100% | 103217.52 |  | 16782.48 |  | completed | 16360.68
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-10 |  | 100% | 217936.06 |  | 22063.94 |  | completed | 20860.49
Sub-Total |  | 770000 | 766232.23 |  |  |  | 649496.29 |  | 120503.71
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 100% | 93436.84 |  | 6563.16 |  | on-going | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 222483.04 |  | 37516.96 |  | completed | 37480.88
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 712185.22 | 37480.88 | 37814.78
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 100% | 94480.7 | 24873 | 25519.3 |  | on-going | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-22 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-22 | 2015-11-22 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-22 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-02-24 | 100% | 11351965.8 |  | 10031.09 |  | completed | 0
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 42129313.09 |  | 18571.74
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48525496.81 |  | 436813.29
BUB Projects
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed
Rehabilitation/ Upgrading of Level III Water Supply/ including Water Treatment |  | 10300000 | 10298810.26 |  |  | 92.96% | 7212611.88 |  | 3087388.12 |  | on-going | 3086198.38
Construction of Evacuation Facility CY 2016 |  | 12000000 | 19997000 |  |  | 66.47% | 8438408.46 |  | 3561591.54 |  | on-going | 11558591.54
Total BUB Projects |  | 32011209.04 | 39921999.75 |  |  |  | 25277209.83 |  | 6733999.21
Other project Funded by NGA
Construction of Early Childhood Care and Development Council Building |  | 2437900 | 2437900 |  |  | 100% | 2300000 |  | 137900 |  | completed | 137900
Certified Correct: | [6 empty] | Approved by:
ELAINE E. RESUSTA, CPA | [8 empty] | EUGENIO B. DATAHAN II
Municipal Accountant- Designate | [8 empty] | Municipal Mayor

## 3rd qtr 2019
FDP Form 6- Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE THIRD QUARTER, CY 2019
Municipality: Pilar, Bohol
Program or Project | Location | Allocation Cost (funds downloaded BEA-DILG fund and LGU counterpart) | Bid Cost (with variation order) | Date Started | Target Completion Date | Project Status |  |  |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred To Date |  | Balance (allocation cost less total cost incurred)
LOCAL FUNDED PROJECTS
Pilar GYMP | Pilar, Bohol | 1200000 | 0 | 2012-11-16 | 2013-06-30 | 67% | 753389.48 |  | 446610.52 |  | on going
Rehab/Repair
Bagumbayan
Public Mkt. | B/bayan, Pilar | 250000 | 0 | 2012-03-08 | 2012-07-15 | 100% | 228323.71 |  | 21676.29 |  | completed
Construction of MDRRMC Building (Phase IV) | Poblacion, Pilar, Bohol | 1395500 | 1395500 | 2017-08-04 | 2017-12-02 | 100% | 1395500 |  | 0 |  | completed
Repair and Rehabilitation of 6.0 KM Estaca-San Isidro-La Suerte FMR | Pilar, Bohol | 500000 | 0 | 2018-11-25 | 2018-12-25 | 100% | 495200 |  | 4800 |  | completed
Improvement and Rehabilitation of .26KM Public Market Access Road | Bagumbayan Pilar, Bohol | 1000000 | 990168.7 | 2018-11-29 | 2019-05-27 | 100% | 860534.01 |  | 139465.99 |  | completed
Improvement of Bagumbayan Access Roadwith Bus Terminal | Bagumbayan Pilar, Bohol | 900000 | 892517.12 | 2019-04-09 | 2019-07-08 | 100% | 840334 |  | 59666 |  | completed
Improvement of San Isidro Public Market | San Isidro, Pilar, Bohol | 403000 |  | 2019-04-09 | 2019-07-08 | 100% | 390812.2 |  | 12187.8 |  | completed
TOTAL |  | 5648500 | 3278185.82 |  |  |  | 4964093.4 | 0 | 684406.6
BEA PROJECTS
Package 1 | [7 empty] | 0
Repair and Rehab of Day Care Center | Proper Buenasuerte, pilar, Bohol | 70000 | 68498.76 | 2015-05-10 | 2015-10-10 | 100% | 51514.3 | 16984.46 | 18485.7 |  | completed | 16984.46
Repair and Rehab of Day Care Center | Inaghuban, Pilar, Bohol | 119999.99 | 118499.98 | 2015-05-10 |  | 100% | 118499.98 |  | 1500.01 |  | completed | 0
Repair and Rehab of Day Care Center | La Suerte, Pilar, Bohol | 240000 | 237999.96 | 2015-05-10 |  | 100% | 237999.95 |  | 2000.05 |  | completed | 0.01
Repair and Rehab of Day Care Center | Lumbay, Pilar, Bohol | 260000 | 257999 | 2015-05-10 |  | 100% | 227279.93 |  | 32720.07 |  | completed | 30719.07
Repair and Rehab of Day Care Center | Lundag, Pilar, Bohol | 240000 | 237999.82 | 2015-05-10 |  | 100% | 206413.05 |  | 33586.95 |  | completed | 31586.77
Sub-Total |  | 929999.99 | 920997.52 |  |  |  | 841707.21 |  | 88292.78
Package 2
Repair and Rehab of Day Care Center | Aurora, Pilar, Bohol | 240000 | 239530 | 2015-05-09 | 2015-10-10 | 100% | 239530 |  | 470 |  | completed | 0
Repair and Rehab of Day Care Center | Mahayahay, Buenasuerte, Pilar, bohol | 70000 | 69202.48 | 2015-05-09 |  | 100% | 69202.48 |  | 797.52 |  | completed | 0
Repair and Rehab of Health Center | Buenasuerte, Pilar, Bohol | 100000 | 99125 | 2015-05-09 |  | 100% | 99125 |  | 875 |  | completed | 0
Repair and Rehab of Health Center | Inaghuban, Pilar, Bohol | 120000 | 119578.2 | 2015-05-09 |  | 100% | 119578.2 |  | 421.8 |  | completed | 0
Repair and Rehab of Health Center | San Isidro, Pilar, Bohol | 240000 | 238796.55 | 2015-05-09 |  | 100% | 238796.55 |  | 1203.45 |  | completed | 0
Sub-Total |  | 770000 | 766232.23 |  |  |  | 766232.23 |  | 3767.77
Package 3 | [8 empty] | 0
Repair and Rehab of Day Care Center | Proper Catagdaan, Pilar, Bohol | 200000 | 199702 | 2015-05-22 | 2015-10-22 | 100% | 199702 |  | 298 |  | completed | 0
Repair and Rehab of Day Care Center | Danao Catagdaan, Pilar, Bohol | 100000 | 99932.84 | 2015-05-22 |  | 100% | 93436.84 |  | 6563.16 |  | completed | 6496
Repair and Rehab of Day Care Center | Sitio Suba estaca, Pilar, Bohol | 120000 | 119918.95 | 2015-05-22 |  | 100% | 118304.25 |  | 1695.75 |  | completed | 1614.7
Repair and Rehab of Day Care Center | San Carlos, Pilar, Bohol | 130000 | 129871.28 | 2015-05-22 |  | 100% | 113836.28 |  | 16163.72 |  | completed | 16035
Repair and Rehab of Day Care Center | San Vicente, Pilar, Bohol | 240000 | 239857 | 2015-05-22 |  | 100% | 239857 |  | 143 |  | completed | 0
Sub-Total |  | 790000 | 789282.07 |  |  |  | 765136.37 |  | 24863.63
Package 4 | [8 empty] | 0
Repair and Rehab of Day Care Center | Del Pilar, Pilar, Bohol | 240000 | 239887.34 | 2015-05-22 | 2015-09-22 | 100% | 239887.34 |  | 112.66 |  | completed | 0
Repair and Rehab of Day Care Center | Ilaud, Pilar, Bohol | 260000 | 259963.92 | 2015-05-22 |  | 100% | 259963.92 |  | 36.08 |  | completed | 0
Repair and Rehab of Day Care Center | Pamacsalan, Pilar, Bohol | 130000 | 129931.68 | 2015-05-22 |  | 100% | 129931.68 | 0 | 68.32 |  | completed | 0
Repair and Rehab of Day Care Center | Rizal, Pilar, Bohol | 120000 | 119883.16 | 2015-05-22 |  | 100% | 119883.16 | 0 | 116.84 |  | completed | 0
|  | 750000 | 749666.1 |  |  |  | 749666.1 | 0 | 333.9
Package 5 | [7 empty] | 0 | 0
Repair and Rehab of Health Center | San Carlos, Pilar, Bohol | 184425.28 | 184386.02 | 2015-08-22 | 2016-02-22 | 100% | 184386.02 | 0 | 39.26 |  | completed | 0
Repair and Rehab of RHU Building | Poblacion, Pilar, Bohol | 500000 | 499784.47 | 2015-08-22 |  | 100% | 399091.61 | 100692.86 | 100908.39 |  | completed | 100692.86
Repair and Rehab of Purok 3 Day Care Building | Poblacion, Pilar, Bohol | 750000 | 749582.57 | 2015-08-22 |  | 100% | 749582.57 | 0 | 417.43 |  | completed | 0
Repair and Rehab of Health Center | Bagumbayan, Pilar, Bohol | 200000 | 199743.01 | 2015-08-22 |  | 100% | 199743.01 | 0 | 256.99 |  | completed | 0
Repair and Rehab of Day Care Center | Bagumbayan, Pilar, Bohol | 200000 | 199765.2 | 2015-08-22 |  | 100% | 199765.2 | 0 | 234.8 |  | completed | 0
Repair and Rehab of Day Care Center | Bagacay, Pilar, Bohol | 260000 | 259433.52 | 2015-08-22 |  | 100% | 259433.52 | 0 | 566.48 |  | completed | 0
Sub-Total |  | 2094425.28 | 2092694.79 |  |  |  | 1992001.93 | 100692.86 | 102423.35 |  | completed
Package 6 | [7 empty] | 0 | 0
Repair and Rehab of Day Care Center | Bayong, Pilar, Bohol | 260000 | 252889.66 | 2015-08-22 | 2016-02-22 | 100% | 252884.66 | 5 | 7115.34 |  | completed | 5
Repair and Rehab of Health Center | Cagawasan, Pilar, Bohol | 130000 | 127866 | 2015-08-22 |  | 100% | 127866 | 0 | 2134 |  | completed | 0
Repair and Rehab of Day Care Center | Cagawasan, Pilar, Bohol | 130000 | 128328.7 | 2015-08-22 |  | 100% | 128328.7 | 0 | 1671.3 |  | completed | 0
Repair and Rehab of Health Center | Cansungay, Pilar, Bohol | 100000 | 99202.54 | 2015-08-22 |  | 100% | 99202.54 | 0 | 797.46 |  | completed | 0
Repair and Rehab of Day Care Center | Cansungay, Pilar, Bohol | 160000 | 159438.3 | 2015-08-22 |  | 100% | 159438.3 | 0 | 561.7 |  | completed | 0
Repair and Rehab of Day Care Center | Proper Estaca, Pilar, Bohol | 120000 | 119353.7 | 2015-08-22 |  | 100% | 94480.7 | 24873 | 25519.3 |  | completed | 24873
Repair and Rehab of Health Center | Pamacsalan, Pilar, Bohol | 130000 | 127120 | 2015-08-22 |  | 100% | 127120 | 0 | 2880 |  | completed | 0
Repair and Rehab of Tantarung Day Care Center | Poblacion, Pilar, Bohol | 100000 | 98512 | 2015-08-22 |  | 100% | 98512 | 0 | 1488 |  | completed | 0
Repair and Rehab of Malinao Day Care Center | Poblacion, Pilar, Bohol | 100000 | 99375.8 | 2015-08-22 |  | 100% | 99375.8 | 0 | 624.2 |  | completed | 0
Repair and Rehab of Health Center | Rizal, Pilar, Bohol | 120000 | 119428 | 2015-08-22 |  | 100% | 119428 | 0 | 572 |  | completed | 0
Repair and Rehab of TESDA Building | Poblacion, Pilar, Bohol | 130000 | 129020 | 2015-08-22 |  | 100% | 129020 | 0 | 980 |  | completed | 0
Sub-Total |  | 1480000 | 1460534.7 |  |  |  | 1435656.7 |  | 44343.3
0
Repair and Rehab of Poblacion Public Market | Poblacion, Pilar, Bohol | 8587771.6 | 8587455.51 | 2015-05-22 | 2015-11-17 | 100% | 8587455.51 |  | 316.09 |  | completed | 0
Repair and Rehab of Bagumbayan Public Market | Bagumbayan, Pilar, Bohol | 17582986.79 | 17582637.17 | 2015-05-23 | 2015-11-17 | 100% | 17582637.17 |  | 349.62 |  | completed | 0
Repair and Rehab of San Isidro Public Market | San Isidro, Pilar, Bohol | 4615129.55 | 4607254.61 | 2015-05-22 | 2015-11-17 | 100% | 4607254.61 |  | 7874.94 |  | completed | 0
Repair and Rehab of Pilar Municipal Hall | Poblacion, Pilar, Bohol | 11361996.89 | 11351965.8 | 2015-08-24 | 2016-04-19 | 100% | 11351965.8 |  | 10031.09 |  | completed | 0
Sub-Total |  | 42147884.83 | 42129313.09 |  |  |  | 42129313.09 |  | 18571.74
Total BEA Projects |  | 48962310.1 | 48908720.5 |  |  |  | 48679713.63 |  | 282596.47
BUB Projects
Construction of CICL Building | Poblacion, Pilar, Bohol | 1585444.14 | 1556523.12 | 2014-12-22 |  | 100% | 1556523.12 | 0 | 28921.02 |  | completed | 0
SEA K Project | San Isidro, Pilar, Bohol | 190000 | 190000 |  |  | 100% | 190000 | 0 | 0 |  | completed | 0
SEA K Project | Del Pilar, Pilar, Bohol | 237500 | 237500 |  |  | 100% | 237500 | 0 | 0 |  | completed | 0
Rehabilitation of 150M bayong to San Carlos FMR | Pilar, Bohol | 829659.67 | 814179.6 | 2014-12-24 |  | 100% | 814179.6 | 0 | 15480.07 |  | completed | 0
Proposed Expansion/ Improvement of Pilar Waterworks System | Ilaud, Pilar, bohol | 6868605.23 | 6827986.77 | 2015-04-29 | 2015-11-24 | 100% | 6827986.77 | 0 | 40618.46 |  | completed
Rehabilitation/ Upgrading of Level III Water Supply/ including Water Treatment |  | 10300000 | 10298810.26 | 2016-12-04 | 2017-08-04 | 100% | 10298813.57 |  | 1186.43 |  | completed | -3.31
Construction of Evacuation Facility CY 2016 |  | 20000000 | 19997000 | 2016-12-04 | 2017-12-04 | 100% | 19997000 |  | 3000 |  | completed | 0
Total BUB Projects |  | 40011209.04 | 39921999.75 |  |  |  | 39922003.06 |  | 89205.98
Other project Funded by NGA
Construction of Early Childhood Care and Development Council Building |  | 2437900 | 2437900 | 2017-02-04 | 2017-05-12 | 100% | 2300000 |  | 137900 |  | completed | 137900
Local Access Road- Local Road Upgrading Estaca to San Isidro Barangay Road | Estaca to San Isidro, Pilar, Bohol | 4128965 | 0 | 2019-03-15 | 2019-09-20 | 95% | 1292112.23 |  | 2836852.77 |  | on-going construction
Local Access Road- Local Road Upgrading San Isidro to La Suerte Barangay Road | San Isidro to La Suerte, Pilar, Bohol | 3288000 | 0 | 2019-03-18 | 2019-09-14 | 100% | 3122066.04 |  | 165933.96 |  | completed
Construction of Filtration System in Barangays Ilaud, Bayong and San Carlos, Pilar, Bohol | Ilaud, Bayong and San Carlos, Pilar, Bohol | 13533000 | 13531500 | 2018-09-24 | 2019-03-29 | 100% | 11532090.97 |  | 2000909.03 |  | completed
Pilar resettlement Project- Phase I | Poblacion, Pilar, Bohol | 15146609.93 |  | 2018-12-17 |  | 76.14% | 2827571.69 |  | 12319038.24 |  | on-going construction
TOTAL |  | 38534474.93 | 15969400 |  |  |  | 21073840.93 | 0 | 17460634
Certified Correct: | [6 empty] | Approved by:
JOE ALFRED REY B. BUSANO, CPA | [8 empty] | EUGENIO B. DATAHAN II
Municipal Accountant | [8 empty] | Acting Municipal Mayor